## Instructions
Quick Start
1. Brainstorm possible activities that will help you validate your critical numbers. Be sure to use the correct language to capture the idea. 2. Estimate the time it will take (from today) to get the results back. 3. Estimate the number of man hours required to complete the work. 4. Assign "certainty points." These are arbitrary points that represent how much risk will be eliminated from your product after this activity is completed. 5. The "cost of certainty" for the activities is calculated for you. Sort your sheet by the "cost of certainty" because these are the activities that will reduce your risk the most and are the cheapest. 6. Now you have a product roadmap - get to work on the task at the top. Before you begin Be sure you have already completed the Product ROI sheet found here:

## Experiments
Activities
Critical Number to validate | Description |  |  |  | Cost of Certainty | Certainty Points | Cost | Hours | Lag (work days from today)
| What we will do to conduct the experiment. Starts with "we will....." | The data that we will gather and how we will analyize it. Starts with "Then we will see if..." | What we expect the data to show. Starts with "we believe...." | How we will interpret the data if it is what we expect. Starts with "and this means...." and end with the critical question ""so we can be more confident <critical question>.
Impact per user | We will research CompetitorX offering for ProductY | Then we will see if our planned pricing is less expensive. | We believe our planned pricing is less than theirs... | and this means that customers will pay $1 per ProductY so we can be more confident in our monthly revevue per user critical number. | 1200 | 1 | 1200 | 1 | 1
Staff needed | We will create a "ping" response version of the router. | Then we will see if it was more difficult than expected. | We believe it will not be more difficult than expected... | and this means that our ability to estimate the work to deploy a small feature is accurate so we can be more confident in our staff needed critical number. | 2800 | 5 | 14000 | 20 | 10
Monthly Revenue per user | We will put two offers in our product for FeatureZ. One will not mention pricing and the other will make pricing prominent. | Then we will see if the sign-up rate for the offer with pricing is as high as the offer without pricing. | We believe sign-up rates will not decrease when our pricing is prominent... | and this means that customers like our pricing model so we can be more confident in our monthly revenue per user critical number. | 12000 | 4 | 48000 | 40 | 40
Monthly Revenue per user | We will review usage in current ProductY offering. | Then we will see if current customers use the feature at least twice per month | We believe customers are making use it at least twice a month | and this indicates that we can be more confident users will use the feature at least 2x per month in the new system so we can be more confident in our monthly revenue per user critical number. | 16000 | 3 | 48000 | 40 | 40
Staff needed | We will implement the provider as a service provider. | Then we will see if it allows movement of funds to and from our bank account and any other bank account in the US. | We believe the provider will allow us to move funds between our bank account and any bank accuont... | and this means that we won't need to build this feature ourselves so we can be more confident in our staff needed critical number. | 20200 | 2 | 40400 | 2 | 40
[5 empty] | 5333.3333 | 3 | 16000 | 5 | 15